CCLE MANAGEMENT CHECKLIST

| Logistic | When | CHECK |
| --- | --- | --- |
| Identify suitable CCLE candidate from the IPC region | 6 weeks before |  |
| If needed, contact a RC/RT from a different region and request CCLE candidate | 6 weeks before |  |
| Share with the Capacity Assistant of the QA team (Paul.nforneh@fao.org) the names of the CCLE candidates for a check of the requirements | 6 weeks before |  |
| Contact informally the CCLE candidate to check availability | 6 weeks before |  |
| Send to the CCLE candidate the official engagement letter (click here for the version in all languages) and the Facilitators/Lead Facilitator TOR (click here for the version in all languages) | 5 weeks before |  |
| Request to the CCLE candidate formal confirmation of participation with his/her supervisor in cc | 4 weeks before |  |
| If needed, instruct the relevant office to raise the TA and provide logistical details | 4 weeks before |  |
| Follow up and inform the CCLE on the following: |  |  |
| Flight booking | 4 weeks before |  |
| VISA requirements and obtainment (anticipation depending on the country) | 4 weeks before |  |
| Suggested accommodation | 4 weeks before |  |
| site of the training and analysis | 4 weeks before |  |
| Airport pick up and daily transfer | 4 weeks before |  |
| If applicable, ensure the CCLE will receive security briefing and security equipment at arrival. | 4 weeks before |  |
| Technical |  |  |
| Some CCLE will be Co-lead (those applying to L3 certification) and others will be Co-Facilitators (those applying to L2 certification). In both cases early engagement in the preparation process should be promoted, ESPECIALLY for the L3 applicant. Remember that a CCLE as a Co-lead should be engaged in all aspect of the training and analysis preparation, implementation and wrap up, including communication product, while a CCLE in charge of co-facilitation should be engaged rather only in technical debates, daily meeting within Co-Facilitators and be responsible of small groups’ analysis. |  |  |
| Organize a skype call with all the CCLE participating to the chosen activity to prepare the mission, including: - Context and security situation, if applicable, workshop logistic and organization of agenda - Review and discussion of the TOR as needed If the CCLE is co-facilitating a training: - Split and attribute training sessions to the CCLE and provide the link to all training materials including presentations, workbook, agenda, relevant tables, etc.. - Open a skype group with all Co-Facilitators including the CCLE where questions on training can be raised If the CCLE is co-facilitating or co-leading an analysis: - IPC in the country: parameters, unit and duration of the analysis, history of IPC in the country, sensitivities, etc.. - Data available and analysis agenda, including procedures for small groups set up and areas split, daily meetings, vetting process, etc… | 2 weeks before |  |
| The CCLE is introduced to the all plenary, taking advantage to present his/her competencies and explaining its role. The CCLE programme should be very quickly explain, to ensure full integration of the person in the analysis team. | At the beginning of the activity |  |
| Ensure CCLE is engaged proactively during the whole duration of the training/analysis. The Lead facilitator acts as a mentor and promotes autonomy as this is the last learning opportunity before the CCLE becomes L2 or L3. In training: - Ensure the CCLE lead/facilitate some training sessions (at least 4) and he/she is asked to reply to participants’ questions, seconded by GSU/L3 staff - Ensure the CCLE lead/facilitate the exercises in small groups and facilitate restitution of the exercise - Ensure CCLE support the wrapping up session (online test, training assessment, etc..) In analysis: - Ensure the CCLE lead/facilitate a small group work. If the CCLE is applying to L3, engage him/her in all technical debate, logistic debate etc.. and ask to lead the daily debrief meeting among Co-Facilitators - If the CCLE is applying to L3, ensure he/she also circulate among groups and is available to answer questions - Ensure the CCLE (L2 or L3) is aware and proactive in taking responsibility of his/her group work, including checking the quality of the analysis in ISS/worksheets, participants list, and highlighting potential challenges to the co-facilitation group, sharing them openly in the Co-Facilitators daily meeting - Ensure the CCLE (L3 applicant) is engaged in plausibility checks or vetting sessions conducted by the Lead Facilitator - Ensure the CCLE (L2 or L3) is engaged in the communication activities (brief preparation) | During the analysis |  |
| Engage the CCLE (L3 applicant) in the brief formulation and revision. | After the analysis |  |
| Wrap up on the CCLE experience |  |  |
| Send a thank you email to all CCLE and to the TWG for welcoming the CCLE | After the analysis |  |
| Fill the CCLE appraisal to assess the candidate readiness for certification (L2 or L3) – click here - | After the analysis |  |
| Request the CCLE to fill the CCLE self assessment tool - click here - (EN/FR) | After the analysis |  |