## Analysis Checklist_v.1
IPC IMPLEMENTATION CHECKLIST
COUNTRY
YEAR
IPC DATE
Task # | Task | Primary Responsibility | Tool used | Timeline | Status | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
1 | Pre-analysis/ Preparation |  |  |  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.1 | Preparation
1.1.1 | Hold a consultative meeting with stakeholders to discuss data collection needs/plans and ensure that IPC evidence requirements will be met in a timely manner (i.e. Indicators and representativeness/unit of analysis) | TWG |  | 3 months before analysis | In progress
1.1.2 | Develop budget to identify financial support needs Seek additional funding for data collection and IPC implementation if needed | TWG CST | Budgeting tool | 3 months before analysis | In progress
1.1.3 | Request support from IPC GSU for training and/or analysis facilitation if needed | TWG chair/co-chair | Email | 1 month before analysis | Not initiated
1.1.4 | Identify: - IPC workshop modality (i.e. Virtual, F2F or Hybrid) - Capacity gaps and training needs (i.e. full Level 1/Tailored/Refresher) - Analysis parameters (date, place, duration of current/projection, unit of analysis, etc..) + Communicate the final decision with GSU using analysis ticket | TWG CST QA | Consolidate data tool for virtual analyses – Sheet ‘Analysis Ticket’ | 1 month before analysis | In progress
1.1.5 | Identify key entities/experts to be invited in the IPC analysis based on clear criteria: - Representation of all relevant sectors and stakeholders - Plurality (especially IPC partners) + Share IPC training/analysis invitations with all relevant partners | TWG CST | Consolidate data tool for virtual analyses – Sheet ‘Analysis Team Matrix ’ + Invitation Email | 1 month before analysis | Not initiated
1.1.6 | Discuss and review previous Self Assessment Tool and/ or Reviews (RTQR, LLE, etc.) recommendations | QA TWG CST | Email | 1 month before analysis | Not initiated
1.1.7 | Develop IPC communication plan (including dissemination) based on IPC communication matrix template | TWG | IPC Country communication plan | 1 month before analysis | Not initiated
1.1.8 | Follow-up on invitations and confirm participation of IPC analysts | TWG |  | 3 weeks before analysis | Not initiated
1.1.9 | Coordinate with LMS team to enrol participants into the LMS platform | Training Lead Facilitator with IM Team |  | 1 week before the training | Not initiated
1.1.10 | Hold final IPC analysis preparation meeting with the Co-Facilitators to: - Finalize agenda - Define sub-groups - Clarify roles and resposnsibilities | TWG | Training/ analysis agenda Consolidate data tool for virtual analyses – Sheet ‘Analysis Team Matrix ’ | 1 week before analysis | Not initiated
1.1.11 | Share references and tools with confirmed participants including: - Previous IPC report - IPC manual - Agenda - Analysts ToR - Training link and login support - Analysis link (if virtual) | TWG | Analysis Team TOR | 1 week before analysis | Not initiated
IPC manual
Agenda
1.2 | Logistics and Financial preparation
1.2.1 | Identify logistical needs: laptops, Venue, Food, transport, visa, internet, etc… | TWG CST |  | 1 month before analysis | Not initiated
1.2.2 | Prepare detailed budget based on IPC training/analysis duration, location and number of participants, including internet needs Note: For virtual workshops, organize internet bundles for analysts if needed | TWG CST | Budgeting tool | 1 month before analysis | Not initiated
1.3 | Technical & Data preparation
1.3.1 | Pre-assess the Reliability Scores of evidence. Where possible/ feasible review data collection methodology (sample, questionnaire design) to ensure compliance with IPC protocols | TWG CST QA | Consolidate data tool for virtual analyses – Sheet ’Data Mapping Matrix ’ | 2 weeks before analysis | Not initiated
1.3.2 | Identify, gather and consolidate relevant datasets and evidence using the IPC data mapping matrix. Verify indicators cut-off are aligned with IPC Reference Table. Identify any data gaps and coordinate with TWG members to fill data gaps(use data from similar nearby areas, use historical evidence). Ensure all datasets are stored in an online shared folder (i.e. Dropbox/ Google Drive, etc.) to gather and share all the raw evidence used for the analysis | TWG CST Lead facilitator | Consolidate data tool for virtual analyses – Sheet ’Data Mapping Matrix ’ | 2 weeks before analysis | Not initiated
1.3.3 | Coordinate with relevant partners (WFP, FSAS, etc.) to complete HFA matrix | TWG CST QA | ISS and Consolidate data tool for virtual analyses – Sheet ’Data Mapping Matrix ’ ( Or ISS version 2) | 3 weeks before analysis | Not initiated
1.3.4 | Request/collect official population data to be used for the analysis | TWG CST |  | 3 weeks before analysis | Not initiated
1.4 | Analysis Platform Preparation
1.4.1 | Set up an ISS/AP preparation task force. Ensure appropriate editing rights are given | Lead facilitator TWG | ISS/AP | 2 weeks before analysis | Not initiated
1.4.2 | Create new analysis in country IPC AP/ISS portal adapting shapefiles based on units of analysis selected, including the correct mapping protocols for urban areas and camps | ISS/AP preparation task force | ISS/AP and Shape Files | 2 weeks before analysis | Not initiated
1.4.3 | Upload population data on ISS/AP using the population table excel template | ISS/AP preparation task force | ISS/AP | 2 weeks before analysis | Not initiated
1.4.4 | Prepare Area Description and HH group definition (if HAG analysis) – STEP 1 | TWG and ISS/AP preparation task force | ISS/AP | 2 weeks before analysis | Not initiated
1.4.5 | Prepare and upload ISS data including: - Evidence statements for outcome indicators using the ISS/AP indicator template - Prepare and organize evidence in the IPC evidence repository – STEP 2 and Repository - Pre-fill evidence statements in IPC Analysis Worksheets – STEP 3 | ISS/AP preparation task force | Outcome template ISS/AP ISS/AP and Consolidate data tool for virtual analyses – Sheet ’Data Mapping Matrix ’ | 1 week before analysis | Not initiated
1.4.6 | Prepare CDT | ISS/AP preparation task force | CDT matrix | 1 week before analysis | Not initiated
1.4.7 | Give or update ISS/AP credentials for the analysts, co-facilitators and Admin. Give appropriate editing rights to analysts. Reset password if required | Lead Facilitator / ISS/AP Administrator | ISS/AP | Day 1 of analysis | Not initiated
2 | IPC Training and Analysis Implementation
2.1 | IPC Training (IPC Level 1 certified/Tailored/Refresher training depending on needs)
2.1.1 | Collect daily signatures of training participants for all days of the training (preferably on one sheet), ensure facilitator(s) and co-facilitators (in-country and CCLE) sign and indicate their roles on the attendance sheet, fill the certification matrix and the CCLE capture sheet | Lead Facilitator QA team | Attendance sheet | All days of training | Not initiated
2.1.2 | Share training material with participants | Training Lead Facilitator | Training material | Day one of training | Not initiated
2.1.3 | Share training evaluation link with participants | Training Lead Facilitator | Training evaluation | Last day of training | Not initiated
2.1.4 | Share online test link with participants | Training Lead Facilitator | Online test | Last day of training | Not initiated
2.2 | IPC Analysis (5-7 days)
2.2.1 | Ensure that facilitator(s) and co-facilitators (in-country and CCLE) sign and indicate their roles on the attendance sheet, fill the certification matrix and the CCLE capture sheet. These should be sent to IPC GSU. | Lead Facilitator | Attendance Sheet | Last day of analysis | Not initiated
2.2.2 | Present the co-facilitators (including CCLE) and explain their role to analysts, share groups composition | TWG Lead Facilitator | Consolidate data tool for virtual analyses – Sheet ‘Analysis Team Matrix ’ | Day one of analysis | Not initiated
2.2.3 | For virtual analysis: - Create a Skype/Zoom/slack/ groups for each analysis team (Ensure to the extent possible the lead facilitator is part of each group) - Create an online coordination group for facilitators to discuss any issues that come up | Lead Facilitator |  | Day one of analysis | Not initiated
2.2.4 | Present main data and information by relevant expert (e.g. assumptions, parameters, etc..) | TWG Lead Facilitator |  | Day one of analysis | Not initiated
2.2.5 | If needed conduct the analysis of one area in plenary to ensure good understanding of interpretation of evidence and of steps of the worksheet | Lead Facilitator |  | Day 2 or 3 of analysis | Not initiated
2.2.6 | Conduct debriefs as needed with co-facilitators and other core TWG members. Identify and address any critical challenges faced. Prepare minutes of daily briefings. | Lead Facilitator |  | All days of analysis | Not initiated
2.2.7 | Conduct a plenary session to discuss and agree on projection assumptions. Upload assumptions on Step 8 | Lead Facilitator | ISS/AP Guidance on preparing projection assumptions | Day 2 or Day 3 | Not initiated
2.2.8 | Validate/vet final IPC results in plenary session (during last day of analysis) Document all comments received during the plenary. | Lead Facilitator |  | Last days of analysis | Not initiated
2.2.9 | Revise areas classification and conclusions based on plenary discussions. | Lead Facilitator Co-facilitators | ISS/AP | Last days of analysis | Not initiated
2.2.10 | Discuss key messages in plenary for the brief (were there improvements, what are the key drivers, how will the brief look like) | Lead Facilitator |  | Last day of analysis | Not initiated
2.2.11 | Clean ISS/AP for reliability score, and check Step 5 HFA is well documented | Lead Facilitator and co-facilitators |  | Last day of analysis | Not initiated
2.2.12 | Discuss and document Self-Assessment Tool in plenary | IPC secretariat | Self-Assessment Tool in ISS/AP | Last day of analysis | Not initiated
2.2.13 | Finalise the CDT matrix and share with QA team for record | Lead Facilitator | CDT matrix | After the analysis | Not initiated
2.3 | Post Analysis
2.3.1 | Check consistency (both in ISS/AP and paper version of the final report) and accuracy of the results (classification, population estimates, etc.) | IPC Secretariat Lead Facilitator | ISS/AP | Last day of analysis | Not initiated
2.3.2 | Convert in PDF population tables and share with TWG or lead facilitators with caveat of possible minor changes if miscalculation | Lead Facilitator IPC secretariat | ISS/AP | Last day of analysis | Not initiated
2.3.3 | Retire ISS/AP rights from participants and share publicly the ISS/AP analysis into the Global Platform | ISS/AP preparation task force | ISS/AP | Last day of analysis | Not initiated
2.4 | IPC Communication/Results Dissemination
2.4.1 | Implement the IPC country communication plan | TWG | IPC Country communication plan filled | Last Day of Analysis | Not initiated
2.4.2 | Present IPC findings to relevant stakeholders/decision-makers | TWG |  | Within 1 week | Not initiated
2.4.3 | Ensure endorsement and official release of IPC results according to established mechanisms (detailed in IPC TWG ToRs) | TWG |  | Within 2-3 weeks of analysis | Not initiated
2.4.4 | Disseminate IPC findings based on IPC communication/dissemination plan | TWG |  | Within 2-3 weeks of analysis | Not initiated
3 | IPC Analysis Capitalization
3.1 | IPC Learning Process
3.1.1 | Hold IPC TWG meeting to discuss lessons learnt/ best practices | TWG |  | Within 1 week | Not initiated
3.1.2 | Document feedback from decision-makers on the IPC process and products and document lessons learnt | TWG |  | Within 1 week | Not initiated
Definitions
IPC secretariat: IPC secretariat is the IPC focal person(s) in country and providing the IPC related support on a day to day basis